## LESSONS LEARNED
LESSONS LEARNED
PROJECT NAME | CC Event Recommender System
PROJECT ID
PROJECT MANAGER | Jayant GS
PROJECT SPONSOR | Cloud Counselage Pvt Ltd
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2020-06-22 | Completed Reasearch on the project | Project plan | If changes occur it needs to be changed | Try to clear out the proper project plan from the respective mentor | developed the idea successfully | Project Manager | Closed | None
2 | 2020-02-07 | Planning of the idea presented above | project managemant | Design may change according to further requirement | None | on the basis of idea I've designed the idea | Project Manager | Closed | None
3 | 2020-10-07 | finalization of data | Technical | proper intended data was expected to be created | proper set of data should be provided by C.c | None | Project Manager | Closed | None
4 | 18/7/2020 | preprocessed and cleaning data | Technical | needs various do and try errors | cleaned data should be provided by mentors | Completed it | Project Manager | Closed | None
5 | 22/7/2020 | Algorithm for classification for employees based on domains and events | Technical | Issue of overfitting | None | after getting a proper data , algorithm part is to be done | Project Manager | Closed | None
6 | 26/7/2020 | Employee name extraction from the dataset using our model | Technical | some of the event name didn't alloted to the employee | Event name should be provided by mentor | from the model finally found out the employee name | Project Manager | Closed | None