## Sheet1
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | CC Event Recommender
PROJECT SPONSOR | Self
PROJECT MANAGER | Jayant G S
EXPECTED START DATE | 2020-06-15
EXPECTED COMPLETION DATE | 2020-07-31
ESTIMATED COST | None
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE | This project will provide solution of making a robust recommender system that will help cloud counselage to invite its employees/interns to be in the events that he/she is interested in, as mentioned in preferences. This will also help organization to save their resources and time. This system will help organization to make all the right resources available to right people.
BUSINESS CASE | Over the years, reaching right thing to right people is challenge. As there are lot of employees/interns and alumini's under cloud counselage's umbrella to help them to grow in their respective professions is always the mission of cloud counselage, so with this system cloud counselage can provide recommendation of right events to right people and thus help everyone grow
GOALS/METRICS | To develop an efficient recommender system that can be used by an organization.
EXPECTED DELIVERABLES | A full fledged system that will help them to provide right recommendation to right people by using machine learning concepts
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE | Static database of employer with preferences and domain set, working on latest Python version(3.7), Auto-generating the final recommedation in the csv file.
OUTSIDE OF SCOPE | Working with real-time databases, Sending mails/sms/notification to the concerned individual for the invitation of the event.
PROJECT RESOURCES AND COSTS
PROJECT TEAM | Keval Shah
SUPPORT RESOURCES | Laptop
SPECIAL NEEDS | None
PROJECT BENEFITS AND CUSTOMERS
PROCESS OWNER | Keval Shah
KEY STAKEHOLDERS | Jayant G S, Nirbhey Singh Pahwa
END CUSTOMER | Cloud Counselage
EXPECTED BENEFIT | A recommender system which helps to get right resources to right people
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS | Technical risk: Forgetting a requirement might cause time and budget overhead, Resource requirement: Interns taking leave for exams or during covid crisis might put the development on hold
ASSUMPTIONS | This is not tested on real-time data.
CONSTRAINTS | Very stringent time for the completion of project