## Sheet1
PROJECT PLAN FOR EXECUTION PHASE
PROJECT NAME | Event Recommedation System
PROJECT MANAGER | JAYANTH G S |  | EXECUTION PHASE START DATE: |  | 2020-06-15
PROJECT DELIVERABLE | Cloud Counselage |  | EXECUTION PHASE END DATE: |  | 2020-07-31
PROJECT SCOPE
PROJECT START DATE | 2020-06-15
PROJECT END DATE | 2020-07-31
OVERALL PROGRESS | Completed
PARENT FEATURE | FEATURES | REQUIRED TIME (IN HRS) | START DATE | END DATE | DURATION IN DAYS | STATUS
1.Problem Pre requisites |  |  | 2020-06-15 | 2020-06-21 | 7 | COMPLETED
1.1) Identify the pre-requisites
1.2)Doing research for the project
2)Planning the Project |  |  | 2020-06-22 | 2020-06-28 | 7 | COMPLETED
2.1 Deciding the objective of the project
2.2)Making SRS and Project Charter
COMPLETED
3)Defining System requirement |  |  | 29-062020 | 2020-07-05 | 7
3.1 Making SRS
3.2)Making Project Plan
4)Development Stage 1 |  |  | 2020-07-06 | 2020-07-13 | 7 | COMPLETED
4.1 Preparing datset
4.2 Data wrangling
5)Development Stage 2 |  |  | 2020-07-13 | 2020-07-20 | 7 | COMPLETED
5.1 Perfoming NLP to extract features
6)Development Stage 3 |  |  | 2020-07-20 | 2020-07-27 | 7 | COMPLETED
6.1) Training and Testing on Algorithm
6.2) Model deployment
6.3)Predicting events
7) Finalization |  |  | 2020-07-27 | 2020-07-31 | 7 | COMPLETED
7.1 Preparing design
7.2)Project deliverables and report