## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 3 | 0 | 2 | 1 | 0 | 0
| Project title: |  |  | Project Id: |  | Project Manager: | Jayant GS |  |  | Assumption | 2 | 0 | 1 | 0 | 1 | 0
[10 empty] | Issue | 4 | 1 | 0 | 0 | 0 | 0
|  |  |  | Last Updated date: | 2020-07-31 | Project Team Lead: | Aarya Bodhankar |  |  | Dependency | 1 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 10 |  |  |  |  | 6
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Database is static | Impact on Training the model | Have a proper set restrictions for adding data in database | Project Manager | High |  | Open | Risk
2 | Risk | Not pertinent data that is used as input | Recommendations will not be accurate | Create proper Datasets of Event as Input | Project Manager | Moderate |  | Open | Assumption
3 | Risk | Having multiple domain | The model will be ambigious | Identify the events before hand involving multiple domains | Project Manager | High |  | Open | Issue
4 | Assumption | Correct Data of the employee is provided for training the mode | Accurate Recommendations | Check the Data before hand | Project Manager | High |  | Open | Dependency
5 | Assumption | Overfitting the model | varied accuracy for recommendations | Precautions must be takel for overfitting | Project Manager | Low |  | Open
6 | Issue | inaccuracy of the model | Irrelevent recommendations | get adequate data and train it properly | Project Manager | High |  | Closed | Open
7 | Issue | Event statements does not contain correct names of events and domains | relevant employee name is not recommended for the events | Apply Lemmatisation in the model | Project Manager | Critical |  | Open | Closed
8 | Dependency | Recommendation Model | recommends employee based on the Event and Domain | Prepare a Proper recommender model | Project Manager | High |  | Closed
9 | Issue | Extracting features | Impact not able to get proper output | apply tokenization to the model | Project Manager | Moderate |  | Closed | Critical
10 | Issue | Clearity in the problem statement | Delay in the start of the projectt | Research on the topic and help from mentor | Project Manager | High |  | Closed | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24